## ProjectPlanningSem3
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
Project Planning Semester 3
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 1 | 3 | 3
Research | 2 | 3 | 6
Plan Document Layout | 1 | 3 | 3
1st Document Draft | 3 | 3 | 9
1st Document Review | 1 | 3 | 3
Document Revision 1 | 1 | 3 | 3
2nd Document Review | 1 | 3 | 3
Document Revision 2 | 1 | 3 | 3
Document Approval | 1 | 3 | 3
|  | Total Man Hours | 36

## UserRequirementsSem4
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
User Requirements Semester 4
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 1 | 3 | 3
First Interview | 1 | 2 | 2
Plan Document Layout | 1 | 3 | 3
Second Interview | 1 | 2 | 2
1st Draft Document | 4 | 3 | 12
1st Document Review | 1 | 3 | 3
Document Revision 1 | 3 | 3 | 9
2nd Document Review | 1 | 3 | 3
Document Revision 2 | 1 | 3 | 3
3rd Document Review | 1 | 3 | 3
Document Revision 3 | 1 | 3 | 3
Document Approval | 1 | 3 | 3
|  | Total Man Hours | 43

## DesignSem4
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
Design Semester 4
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 1 | 3 | 3
Plan Document Layout | 1 | 3 | 3
1st Draft Document | 3 | 3 | 9
1st Document Review | 1 | 2 | 2
Document Revision 1 | 3 | 3 | 9
2nd Document Review | 1 | 3 | 3
Document Revision 2 | 3 | 3 | 9
3rd Document Review | 1 | 3 | 3
Document Revision 3 | 1 | 3 | 3
Document Approval | 1 | 3 | 3
|  | Total Man Hours | 47

## DatabaseTables
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
Database Tables Semester 4
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 1 | 3 | 3
1st Draft Tables (UN) | 1 | 3 | 3
1st Table Review | 1 | 3 | 3
1st Normal Form | 1 | 3 | 3
2nd Normal Form | 1 | 3 | 3
3rd Normal Form | 1 | 3 | 3
Final Table Review | 1 | 3 | 3
Table Approval | 1 | 3 | 3
|  | Total Man Hours | 24

## UserManualDesignSem4
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
User Manual Design Semester 4
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 1 | 3 | 3
Plan Document Layout | 1 | 3 | 3
1st Draft Document | 4 | 3 | 12
1st Document Review | 2 | 2 | 4
Document Revision 1 | 3 | 3 | 9
2nd Document Review | 1 | 3 | 3
Document Revision 2 | 3 | 3 | 9
3rd Document Review | 1 | 3 | 3
Document Revision 3 | 1 | 3 | 3
Document Approval | 1 | 3 | 3
|  | Total Man Hours | 52

## CodingSem4
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
Coding (Java) Semester 4
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 2 | 3 | 6
Create Tables | 1 | 1 | 1
Fill Tables (Test Data) | 4 | 2 | 8
Test Tables With SQL | 2 | 1 | 2
Code GUI | 10 | 3 | 30
Code Walk Gui | 2 | 3 | 6
Test Gui | 2 | 3 | 6
Code Methods | 8 | 3 | 24
Code Walk Methods | 2 | 3 | 6
Test Methods | 3 | 3 | 9
Code Exceptions | 6 | 3 | 18
Code Walk Exceptions | 2 | 3 | 6
Test Exceptions | 8 | 3 | 24
Connect to Database | 1 | 3 | 3
System Walk Through | 3 | 3 | 9
System Testing | 5 | 3 | 15
|  | Total Man Hours | 173

## UserManualSem4
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
User Manual Semester 4
Description | Duration in Hours | Number Persons | Total Hours
Initial Meeting | 1 | 3 | 3
Draft Document | 3 | 2 | 6
1st Document Review | 1 | 3 | 3
Document Revision 1 | 2 | 2 | 4
2nd Document Review | 1 | 3 | 3
Write HTML Code | 4 | 2 | 8
Test Online Manual | 2 | 3 | 6
Document Approval | 1 | 3 | 3
|  | Total Man Hours | 36

## ProjectSumary
Second Year Project 2011/2012
Automated Payroll System
James Madden | X00086390
Shane Murphy | X00085315
Maciej Macierzynski | X00086366
Project Sumary
Description | Man Hours
Project Planning Semester 3 | 36
User Requirements | 43
Design | 47
Database Tables | 24
User Manual Design | 52
Coding | 173
User Manual Design | 36
Total Project Man Hours | 411 | Hours
Per Person (3 Persons) | 137 | Hours
37 hour week | 3.7027 | Weeks